# Answer for Question 3.1

In Question 3.1, the task was to enter the Work Breakdown Structure (WBS) hierarchy into ProjectLibre, assign resources, durations, predecessors, and costs. Below is a detailed explanation of the steps followed:

## Step 1: Entering the WBS Hierarchy

I copied the full WBS provided into the Task Sheet (Gantt Chart view) in ProjectLibre. Using the Indent button, I created the hierarchy as follows:
- Level 1: Health & Wellness App (the overall project)
- Level 2: Major phases (e.g., Project Planning & Requirements, Design & Prototyping, Backend Development, etc.)
- Level 3: Sub-tasks under each phase (e.g., Gather Requirements, Define Scope, Risk Assessment).

## Step 2: Adding Resources

In the Resource Sheet, I created four resources:
- TK (Work resource)
- Wambo (Work resource)
- KG (Work resource)
- Thando (Work resource)

All resources were set to 100% availability. Resources were then assigned to the relevant sub-tasks in the Task Sheet under the 'Resource Names' column.

## Step 3: Durations

Each task was given a suitable duration instead of the default 1 day. For example:
- Gather Requirements → 10 days
- Define Scope → 5 days
- API Development → 15 days
- Integration Testing → 7 days
These durations were applied to ensure a realistic project timeline.

## Step 4: Predecessors (Dependencies)

Dependencies between tasks were entered in the 'Predecessors' column. For example:
- Define Scope depends on Gather Requirements.
- Risk Assessment depends on Gather Requirements.
- Prototype Building depends on Initial Sketches.
- Integration Testing depends on UI Implementation and Functionality Coding.

This created a logical flow of tasks in the Gantt chart.

## Step 5: Entering Costs

I inserted the Fixed Cost column and entered the provided budgets for each sub-task. For example:
- Gather Requirements → $140,000 (equivalent to R140,000)
- Define Scope → $70,000 (R70,000)
- Risk Assessment → $70,000 (R70,000)

Costs were only entered for sub-tasks, and ProjectLibre automatically rolled them up into summary tasks and then into the overall project total. The total project budget was $1,750,000 (representing R1,750,000).

## Step 6: Final Review

After entering the hierarchy, durations, resources, predecessors, and costs, I verified that:
- The WBS hierarchy displayed correctly with indented sub-tasks.
- All resources were correctly assigned.
- The Gantt chart showed a proper sequence of tasks.
- The total cost rolled up to $1,750,000 (R1,750,000).

Screenshots of the Task Sheet, Gantt chart, Resource Sheet, and cost roll-ups were taken as evidence.